## Sheet1
Change control log
Change ID | Date Submitted | Submitted By | Description | Reason / Justification | Impact Analysis | Priority | Status | Approved By, Date
1 | 2026-07-02 | Student | Forgot Password feature | Easy account recovery | DB update, UI change, 1 extra day | High | Approved | Project Manager, 02-Jul-2026
2 | 2026-07-03 | Examination Controller | PDF Roll Number Slip | Easy download | PDF module, 2 extra days | High | Approved | Project Manager, 03-Jul-2026
3 | 2026-07-05 | Accounts Officer | Mobile Fee Payment | Faster fee submission | Payment gateway, 4 extra days | High | Approved | Project Manager, 05-Jul-2026
4 | 2026-07-07 | Teacher | Edit Marks option | Fix entry mistakes | DB update, 2 extra days | Medium | Approved | Project Manager, 07-Jul-2026
5 | 2026-07-09 | Admin | SMS/Email Results | Quick student alerts | Notification API, 3 extra days | Medium | Approved | Project Manager, 09-Jul-2026